SIX-SPRINT DELIVERY DOCUMENT

SIMPLOS — Common Core First + Vertical Extensions

Timeline assessment: 6 sprints × 14 days = 84 calendar days. The delivery strategy is intentionally architecture-first: Sprints 1–4 build reusable/common capabilities; Sprint 5 adds Liquor-specific capabilities; Sprint 6 adds Grocery-specific capabilities.

# Architecture Strategy

The objective is to avoid building separate POS products for each retail segment. Common capabilities should be implemented once as configurable engines/modules. Vertical-specific requirements should be delivered as configuration, extensions, workflows and integrations on top of that core.

| Layer | Scope |
| --- | --- |
| Common Core | Authentication, tenant/location model, product master, POS engine, pricing, tax foundation, transactions, inventory, suppliers, purchasing, receiving, Back Office, reporting, integrations, hardware abstraction, audit/security. |
| Liquor Extension | Age verification, restricted products, ID scanner, pack/case/UPC behavior, deposits/charges and liquor-specific compliance. |
| Grocery Extension | Weighted products, scales, weighted barcodes, grocery units/packaging, perishables if approved and grocery-specific workflows. |
| Future Extensions | Restaurant, convenience and specialty retail should reuse the same common core rather than create separate foundations. |

# Sprint 1 — Common Platform Foundation

Duration: Day 1–Day 14

## Work Items

Multi-tenant architecture: Platform → Business → Location → Register/Device.

Authentication, users, roles and permissions foundation.

Core database/data model and service/API architecture.

Business/location configuration and common settings.

Product master foundation: SKU, barcode/UPC, category, brand, unit, pack configuration, cost, retail price, tax category, active/inactive.

Common audit trail, logging, error handling and observability foundation.

Development, QA and deployment environments.

UX/design system and reusable application components.

## Deliverables

Common platform architecture

Authentication/RBAC foundation

Tenant/location/register model

Product master foundation

Reusable UI/API components

Audit/logging foundation

Dev/QA environment

## Definition of Done

Feature implemented on the common platform or vertical extension without unnecessary duplication.

Acceptance criteria demonstrated using representative scenarios.

Relevant functional/integration tests completed.

Existing common functionality is regression-tested after vertical changes.

RBAC/audit requirements applied where applicable.

Sprint demo and client review completed.

Open dependencies and decisions documented.

# Sprint 2 — Common POS & Transaction Engine

Duration: Day 15–Day 28

## Work Items

POS login and register opening/closing.

Product search, barcode scanning and reusable cart engine.

Quantity, item removal, hold/retrieve and common transaction controls.

Common pricing engine: regular, location, promotional, quantity-based and sale pricing.

Tax engine foundation with configurable rules.

Customer profile foundation.

Receipt generation, lookup and reprint.

Core transaction ledger and event model.

## Deliverables

Reusable POS transaction engine

Register/session management

Product scan/search/cart

Pricing/tax engine foundation

Customer/receipt foundation

Transaction/audit framework

## Definition of Done

Feature implemented on the common platform or vertical extension without unnecessary duplication.

Acceptance criteria demonstrated using representative scenarios.

Relevant functional/integration tests completed.

Existing common functionality is regression-tested after vertical changes.

RBAC/audit requirements applied where applicable.

Sprint demo and client review completed.

Open dependencies and decisions documented.

# Sprint 3 — Common Inventory, Purchasing & Back Office

Duration: Day 29–Day 42

## Work Items

Inventory by location, sale deduction, receiving increase, adjustments, physical counts and inventory history.

Low-stock/reorder threshold foundation.

Supplier master and supplier-product mapping.

Purchase order foundation, statuses and history.

Receiving foundation: full/partial receipt, discrepancies, damage and substitutions.

Supplier cost history.

Common Web Back Office modules for products, inventory, suppliers, purchasing, locations and users.

Common reporting/export framework.

## Deliverables

Inventory engine

Supplier and supplier-product management

PO/receiving foundation

Cost history

Common Back Office

Reporting/export foundation

## Definition of Done

Feature implemented on the common platform or vertical extension without unnecessary duplication.

Acceptance criteria demonstrated using representative scenarios.

Relevant functional/integration tests completed.

Existing common functionality is regression-tested after vertical changes.

RBAC/audit requirements applied where applicable.

Sprint demo and client review completed.

Open dependencies and decisions documented.

# Sprint 4 — Common Integrations, AI Foundation & Release Core

Duration: Day 43–Day 56

## Work Items

Payment abstraction layer and integration framework; selected provider implementation depends on client/vendor details.

Hardware abstraction layer for scanner, printer, cash drawer, customer display, scale and other supported devices.

Common notification framework.

Integration layer for external services.

Invoice document ingestion and common document-processing pipeline foundation.

AI extraction/matching service architecture and human-review framework.

Offline/sync architecture baseline and transaction integrity controls.

Security hardening, tenant isolation, performance baseline, automated testing and common release pipeline.

## Deliverables

Integration/hardware framework

Payment abstraction

AI/document-processing foundation

Offline/sync foundation

Security/performance baseline

Reusable release pipeline

Common platform release candidate

## Definition of Done

Feature implemented on the common platform or vertical extension without unnecessary duplication.

Acceptance criteria demonstrated using representative scenarios.

Relevant functional/integration tests completed.

Existing common functionality is regression-tested after vertical changes.

RBAC/audit requirements applied where applicable.

Sprint demo and client review completed.

Open dependencies and decisions documented.

# Sprint 5 — Liquor Vertical

Duration: Day 57–Day 70

## Work Items

Age-restricted product configuration and age-verification workflow.

Liquor-specific single/pack/case product and UPC handling.

ID scanner integration where confirmed and technically available.

Deposit/additional charge rules where applicable.

Liquor-specific tax/charge configuration where required.

Liquor-specific compliance/audit fields and reports.

Liquor-specific POS prompts and permissions.

Liquor-specific UAT scenarios and regression against common platform.

## Deliverables

Liquor configuration layer

Age verification

Pack/case/UPC handling

ID scanner integration where applicable

Deposits/additional charges

Liquor reports/audit

Liquor UAT and release

## Definition of Done

Feature implemented on the common platform or vertical extension without unnecessary duplication.

Acceptance criteria demonstrated using representative scenarios.

Relevant functional/integration tests completed.

Existing common functionality is regression-tested after vertical changes.

RBAC/audit requirements applied where applicable.

Sprint demo and client review completed.

Open dependencies and decisions documented.

# Sprint 6 — Grocery Vertical

Duration: Day 71–Day 84

## Work Items

Grocery-specific weighted product workflows.

Weighing-scale integration where confirmed.

Weighted barcode support.

Grocery-specific product/unit/pack configurations.

Grocery-specific inventory and pricing scenarios.

Fresh/perishable handling rules if confirmed by client.

Grocery-specific reports and operational workflows.

Grocery-specific UAT and regression against common platform.

Prepare reusable vertical architecture so future restaurant/convenience/specialty modules can be added without changing the core.

## Deliverables

Grocery configuration layer

Weighted products

Scale integration where applicable

Weighted barcode support

Grocery workflows/reports

Grocery UAT and release

Reusable vertical extension framework

## Definition of Done

Feature implemented on the common platform or vertical extension without unnecessary duplication.

Acceptance criteria demonstrated using representative scenarios.

Relevant functional/integration tests completed.

Existing common functionality is regression-tested after vertical changes.

RBAC/audit requirements applied where applicable.

Sprint demo and client review completed.

Open dependencies and decisions documented.

# Vertical Extension Principle

Do not fork the POS or inventory codebase for Liquor/Grocery.

Common engines should expose configurable rules and extension points.

Vertical requirements should be isolated behind configuration, feature flags, domain services or integration adapters.

Any requirement that changes the common business model should be reviewed before implementation because it may affect all verticals.

Restaurant should be treated as a future vertical extension unless the client explicitly changes the six-sprint scope.

# Key Client Clarifications for This Strategy

Confirm the first two verticals after the common core: Liquor and Grocery.

Confirm whether Restaurant is a future phase or must be included in the six-sprint timeline.

Confirm which capabilities are genuinely common versus vertical-specific.

Confirm whether weighted products are required only for Grocery or also for other verticals.

Confirm whether age verification and liquor compliance vary by jurisdiction.

Confirm whether payment/hardware integrations are common across all verticals.

Confirm whether the same product master and inventory model should support all future verticals.